## Sheet1
Week | Backend | Level | Frontend | Level
2023-05-22 | Set up project environment | Low | Set up project environment | Low
2023-05-29 | Build database schema and models | Medium | Design homepage layout | Low
2023-06-05 | Develop user authentication | Medium | Implement responsive design | Medium
2023-06-12 | Implement RESTful APIs | High | Create login page | Low
2023-06-19 |  |  | Develop registration functionality | Medium
2023-06-26 | Implement data validation and error handling | Low | Build user dashboard | Medium
2023-07-03 | Develop backend logic and business rules | High
2023-07-10 |  |  | Add user profile management | Medium
2023-07-17 | Perform performance testing and optimization | Medium
2023-07-24 |  |  | Implement search functionality | Low
2023-07-31 | Deploy on Azure | Low | Optimize application for mobile devices | High
2023-08-07 | Write API documentation | Low | Deploy on Azure | Low
| Goals |  | Goals
| ML API |  | Visually appealing and intuitive UI
| Database |  | Smooth and responsive user interactions
| Logging and error tracking |  | Good performance and loading times
| Deploy application on Azure |  | Deploy application on Azure
API documentation
Q2 plan | Set up and implement logic for project
Q3 plan | Release project and Deploy on Azure.
Yearyly plan | Refactor and migrate code. Implement new future and maintenance