## Sheet1
Week | Backend | Frontend
2023-05-22 | Set up project environment | Set up project environment
2023-05-29 | Build database schema and models | Design homepage layout
2023-06-05 | Develop user authentication | Implement responsive design
2023-06-12 | Implement RESTful APIs | Create login page
2023-06-19 |  | Develop registration functionality
2023-06-26 | Implement data validation and error handling | Build user dashboard
2023-07-03 | Develop backend logic and business rules
2023-07-10 |  | Add user profile management
2023-07-17 | Perform performance testing and optimization
2023-07-24 |  | Implement search functionality
2023-07-31 | Deploy on Azure | Optimize application for mobile devices
2023-08-07 | Write API documentation | Deploy on Azure
| Goals | Goals
| ML API | Visually appealing and intuitive UI
| Database | Smooth and responsive user interactions
| Logging and error tracking | Good performance and loading times
| Deploy application on Azure | Deploy application on Azure
API documentation